## Dashboard
GHL ARCHITECT DASHBOARD | [7 empty] | Melanie Elver |  |  |  | Apr 1 – Apr 30, 2026
30-Day CRM Mastery Program · Apr 1 – Apr 30, 2026
DAYS COMPLETE |  |  |  | COMPLETION |  |  |  | HOURS LOGGED |  |  |  | PACE STATUS
ON TRACK
of 30 days |  |  |  | target: 100% | [7 empty] | Day 1 of 30
⬡ WEEKLY PROGRESS | [7 empty] | ⬡ MODULE MASTERY
WEEK | DAYS | DONE | TOTAL MIN | PROGRESS | STATUS |  |  | MODULE | DONE | TOTAL | PROGRESS | STATUS
Week 1 | Days 1-7 | [6 empty] | M0: Start Here
Week 2 | Days 8-14 | [6 empty] | M1: Foundation
Week 3 | Days 15-21 | [6 empty] | M2: Setup & Config
Week 4 | Days 22-30 | [6 empty] | M3: Contacts & Data
M4: Build Assets
M5: Sales Tools
M6: Pipeline
M7: Automation
M8: Go Live
M9: Dashboard
⬡ MILESTONES | [7 empty] | ⬡ SKILL ASSESSMENT
# | MILESTONE |  | TARGET | STATUS | DATE |  |  | SKILL |  | RATING | VISUAL
1 | GHL Account Created |  | Day 5 | ⬜ |  |  |  | CRM Strategy |  | 1
2 | 100K Workshop Complete |  | Day 7 | ⬜ |  |  |  | Contact Management |  | 1
3 | First Funnel Published |  | Day 20 | ⬜ |  |  |  | Funnel Building |  | 1
4 | Pipeline Configured |  | Day 25 | ⬜ |  |  |  | Email Marketing |  | 1
5 | First Automation Live |  | Day 28 | ⬜ |  |  |  | Pipeline Management |  | 1
6 | Account Goes Live |  | Day 29 | ⬜ |  |  |  | Automation Design |  | 1
7 | 🎓 GRADUATION |  | Day 30 | ⬜ |  |  |  | Calendar Setup |  | 1
[8 empty] | Reporting |  | 1
[8 empty] | Client Onboarding |  | 1
ARCHITECT SCORE
⬡ 30-DAY STUDY LOG
DAY | DATE | BUDGET | MODULE | LESSONS | TYPE | VID | TASK | TOTAL | FOCUS THEME | STATUS | ACTUAL | NOTES
1 | 2026-04-01 | 1h 00m | Start Here + M0 | L1 Welcome + L2 How To + M0-L1 | Watch | 46 | 14 | 60 | Big Picture | 🔄 In Progress
2 | 2026-04-02 | 1h 00m | Module 0 | M0-L2/L3/L4 + Quiz | Watch+Quiz | 50 | 10 | 60 | Business Models | ✅ Complete | 58
3 | 2026-04-03 | 1h 00m | Module 1 | M1-L1/L2/L3 | Watch | 52 | 8 | 60 | Mindset Before Automation | ⬜ Not Started
4 | 2026-04-04 | 1h 00m | Module 1 | M1-L3.1 Build Process Map | Assignment | 0 | 60 | 60 | YOUR Process Map | ⬜ Not Started
5 | 2026-04-05 | 1h 00m | M1→M2 | M1-L5 + M2-1.1/1.2/1.3 | Watch+Do | 20 | 40 | 60 | First GHL Setup | ⬜ Not Started
6 | 2026-04-06 | 2h 00m | Module 1 | 100K Workshop Part 1 | Workshop | 120 | 0 | 120 | Full CRM Picture | ⬜ Not Started
7 | 2026-04-07 | 2h 00m | Module 1 | 100K Workshop Part 2 + Review | Workshop+Review | 96 | 24 | 120 | CRM Blueprint | ⬜ Not Started
8 | 2026-04-08 | 0h 52m | Module 2 | Users/Permissions + Domains | Watch+Do | 32 | 20 | 52 | Users & Domains | ⬜ Not Started
9 | 2026-04-09 | 0h 59m | Module 2 | Domain Connect + Email Sub-Domain | Watch+Do | 29 | 30 | 59 | Deliverability | ⬜ Not Started
10 | 2026-04-10 | 1h 00m | Module 2 | Integrations Google/Facebook | Watch+Do | 30 | 30 | 60 | Core Integrations | ⬜ Not Started
11 | 2026-04-11 | 1h 00m | Module 2 | Zapier + A2P SMS | Watch | 51 | 9 | 60 | 3rd Party + SMS | ⬜ Not Started
12 | 2026-04-12 | 1h 00m | Module 2 | Phone + Email Systems | Watch | 58 | 2 | 60 | Phone & Email | ⬜ Not Started
13 | 2026-04-13 | 1h 19m | Module 2 | Payment + Brand Board + Quiz | Watch+Do+Quiz | 49 | 30 | 79 | M2 Complete! | ⬜ Not Started
14 | 2026-04-14 | 1h 34m | Module 3 | Contacts Manual + Import + Custom Fields | Watch+Do | 49 | 45 | 94 | Contacts Into GHL | ⬜ Not Started
15 | 2026-04-15 | 0h 55m | Module 3 | Custom Fields + Values | Watch+Do | 35 | 20 | 55 | Data Structure | ⬜ Not Started
16 | 2026-04-16 | 0h 59m | M3→M4 | Custom Values + First Form | Do+Watch+Do | 19 | 40 | 59 | Values + First Form | ⬜ Not Started
17 | 2026-04-17 | 0h 58m | Module 4 | Surveys + Quizzes + Calendar Intro | Watch+Do | 38 | 20 | 58 | Surveys & Calendar | ⬜ Not Started
18 | 2026-04-18 | 1h 00m | Module 4 | Calendar Config + Build | Watch+Do | 38 | 22 | 60 | Booking Calendar | ⬜ Not Started
19 | 2026-04-19 | 1h 00m | Module 4 | Funnel Theory + Watch Build | Watch | 60 | 0 | 60 | Funnel Theory | ⬜ Not Started
20 | 2026-04-20 | 1h 42m | Module 4 | Funnel Build + Chat Widget | Watch+Do | 42 | 60 | 102 | BUILD First Funnel! | ⬜ Not Started
21 | 2026-04-21 | 1h 24m | M4→M5 | QR Codes + SMS/Email Templates | Watch+Do | 44 | 40 | 84 | QR + Sales Assets | ⬜ Not Started
22 | 2026-04-22 | 0h 49m | Module 5 | Email Snippets + Templates | Do+Watch | 29 | 20 | 49 | Email Deep Dive | ⬜ Not Started
23 | 2026-04-23 | 1h 00m | Module 5 | Email Templates + Documents | Do+Watch+Do | 20 | 40 | 60 | Documents & Contracts | ⬜ Not Started
24 | 2026-04-24 | 0h 51m | M5→M6 | Trigger Links + Pipeline Theory | Watch+Do | 36 | 15 | 51 | Links + Pipeline | ⬜ Not Started
25 | 2026-04-25 | 1h 00m | Module 6 | Pipeline + Opportunities | Watch+Do | 35 | 25 | 60 | BUILD Pipeline! | ⬜ Not Started
26 | 2026-04-26 | 1h 00m | Module 7 | Automation & Workflows Theory | Watch+Notes | 43 | 17 | 60 | Automation Mindset | ⬜ Not Started
27 | 2026-04-27 | 1h 40m | Module 7 | Workflow Builder + Knowledge Check | Watch+Check | 88 | 12 | 100 | Automation in Action | ⬜ Not Started
28 | 2026-04-28 | 1h 25m | Module 7 | Build & Test Automation | BUILD | 5 | 80 | 85 | BUILD Automation! | ⬜ Not Started
29 | 2026-04-29 | 1h 00m | M7→M8 | Go Live + Conversations + Invoices | GoLive+Watch | 43 | 17 | 60 | You're LIVE! | ⬜ Not Started
30 | 2026-04-30 | 1h 46m | M8+M9 | Products + Coupons + Dashboard + Final Quiz | Watch+Do+Quiz | 66 | 40 | 106 | GRADUATION DAY! | ⬜ Not Started
⬡ PRE-FLIGHT CHECKLIST
# | ITEM |  |  |  | STATUS
1 | GHL account created & verified |  |  |  | ✗
2 | Custom domain connected |  |  |  | ✗
3 | Email deliverability configured |  |  |  | ✗
4 | Google & Facebook integrated |  |  |  | ✗
5 | A2P SMS registration complete |  |  |  | ✗
6 | Contact import done (50+ contacts) |  |  |  | ✗
7 | First funnel published & tested |  |  |  | ✗
8 | Pipeline with 3+ stages built |  |  |  | ✗
9 | Automation workflow tested end-to-end |  |  |  | ✗
10 | Final quiz passed — CERTIFIED! 🎓 |  |  |  | ✗

## Study Data
Day | Date | Time Budget | Module | Lessons | Type | Video Min | Task Min | Total Min | Focus Theme | Status | Actual Time | Notes | Done Criteria
1 | 2026-04-01 | 1h 00m | Start Here + M0 | L1 Welcome + L2 How To + M0-L1 | Watch | 46 | 14 | 60 | Big Picture | 🔄 In Progress |  |  | Watch all 3 lessons
2 | 2026-04-02 | 1h 00m | Module 0 | M0-L2/L3/L4 + Quiz | Watch+Quiz | 50 | 10 | 60 | Business Models | ✅ Complete | 58 |  | Pass M0 Quiz
3 | 2026-04-03 | 1h 00m | Module 1 | M1-L1/L2/L3 | Watch | 52 | 8 | 60 | Mindset Before Automation | ⬜ Not Started |  |  | Watch M1 intro lessons
4 | 2026-04-04 | 1h 00m | Module 1 | M1-L3.1 Build Process Map | Assignment | 0 | 60 | 60 | YOUR Process Map | ⬜ Not Started |  |  | Complete process map
5 | 2026-04-05 | 1h 00m | M1→M2 | M1-L5 + M2-1.1/1.2/1.3 | Watch+Do | 20 | 40 | 60 | First GHL Setup | ⬜ Not Started |  |  | GHL account created
6 | 2026-04-06 | 2h 00m | Module 1 | 100K Workshop Part 1 | Workshop | 120 | 0 | 120 | Full CRM Picture | ⬜ Not Started |  |  | Complete Part 1
7 | 2026-04-07 | 2h 00m | Module 1 | 100K Workshop Part 2 + Review | Workshop+Review | 96 | 24 | 120 | CRM Blueprint | ⬜ Not Started |  |  | Blueprint document done
8 | 2026-04-08 | 0h 52m | Module 2 | Users/Permissions + Domains | Watch+Do | 32 | 20 | 52 | Users & Domains | ⬜ Not Started |  |  | Users configured
9 | 2026-04-09 | 0h 59m | Module 2 | Domain Connect + Email Sub-Domain | Watch+Do | 29 | 30 | 59 | Deliverability | ⬜ Not Started |  |  | Domain verified
10 | 2026-04-10 | 1h 00m | Module 2 | Integrations Google/Facebook | Watch+Do | 30 | 30 | 60 | Core Integrations | ⬜ Not Started |  |  | Both connected
11 | 2026-04-11 | 1h 00m | Module 2 | Zapier + A2P SMS | Watch | 51 | 9 | 60 | 3rd Party + SMS | ⬜ Not Started |  |  | A2P registered
12 | 2026-04-12 | 1h 00m | Module 2 | Phone + Email Systems | Watch | 58 | 2 | 60 | Phone & Email | ⬜ Not Started |  |  | Phone number active
13 | 2026-04-13 | 1h 19m | Module 2 | Payment + Brand Board + Quiz | Watch+Do+Quiz | 49 | 30 | 79 | M2 Complete! | ⬜ Not Started |  |  | Pass M2 Quiz
14 | 2026-04-14 | 1h 34m | Module 3 | Contacts Manual + Import + Custom Fields | Watch+Do | 49 | 45 | 94 | Contacts Into GHL | ⬜ Not Started |  |  | Contacts imported
15 | 2026-04-15 | 0h 55m | Module 3 | Custom Fields + Values | Watch+Do | 35 | 20 | 55 | Data Structure | ⬜ Not Started |  |  | Custom fields set up
16 | 2026-04-16 | 0h 59m | M3→M4 | Custom Values + First Form | Do+Watch+Do | 19 | 40 | 59 | Values + First Form | ⬜ Not Started |  |  | First form live
17 | 2026-04-17 | 0h 58m | Module 4 | Surveys + Quizzes + Calendar Intro | Watch+Do | 38 | 20 | 58 | Surveys & Calendar | ⬜ Not Started |  |  | Survey created
18 | 2026-04-18 | 1h 00m | Module 4 | Calendar Config + Build | Watch+Do | 38 | 22 | 60 | Booking Calendar | ⬜ Not Started |  |  | Calendar booking works
19 | 2026-04-19 | 1h 00m | Module 4 | Funnel Theory + Watch Build | Watch | 60 | 0 | 60 | Funnel Theory | ⬜ Not Started |  |  | Theory notes complete
20 | 2026-04-20 | 1h 42m | Module 4 | Funnel Build + Chat Widget | Watch+Do | 42 | 60 | 102 | BUILD First Funnel! | ⬜ Not Started |  |  | Funnel published
21 | 2026-04-21 | 1h 24m | M4→M5 | QR Codes + SMS/Email Templates | Watch+Do | 44 | 40 | 84 | QR + Sales Assets | ⬜ Not Started |  |  | Templates saved
22 | 2026-04-22 | 0h 49m | Module 5 | Email Snippets + Templates | Do+Watch | 29 | 20 | 49 | Email Deep Dive | ⬜ Not Started |  |  | 3 email templates
23 | 2026-04-23 | 1h 00m | Module 5 | Email Templates + Documents | Do+Watch+Do | 20 | 40 | 60 | Documents & Contracts | ⬜ Not Started |  |  | Contract template done
24 | 2026-04-24 | 0h 51m | M5→M6 | Trigger Links + Pipeline Theory | Watch+Do | 36 | 15 | 51 | Links + Pipeline | ⬜ Not Started |  |  | Trigger links active
25 | 2026-04-25 | 1h 00m | Module 6 | Pipeline + Opportunities | Watch+Do | 35 | 25 | 60 | BUILD Pipeline! | ⬜ Not Started |  |  | Pipeline configured
26 | 2026-04-26 | 1h 00m | Module 7 | Automation & Workflows Theory | Watch+Notes | 43 | 17 | 60 | Automation Mindset | ⬜ Not Started |  |  | Notes documented
27 | 2026-04-27 | 1h 40m | Module 7 | Workflow Builder + Knowledge Check | Watch+Check | 88 | 12 | 100 | Automation in Action | ⬜ Not Started |  |  | Knowledge check passed
28 | 2026-04-28 | 1h 25m | Module 7 | Build & Test Automation | BUILD | 5 | 80 | 85 | BUILD Automation! | ⬜ Not Started |  |  | Automation tested
29 | 2026-04-29 | 1h 00m | M7→M8 | Go Live + Conversations + Invoices | GoLive+Watch | 43 | 17 | 60 | You're LIVE! | ⬜ Not Started |  |  | Account live
30 | 2026-04-30 | 1h 46m | M8+M9 | Products + Coupons + Dashboard + Final Quiz | Watch+Do+Quiz | 66 | 40 | 106 | GRADUATION DAY! | ⬜ Not Started |  |  | Final quiz passed

## Calc Engine (hidden)
METRIC | VALUE | Week | Done | Total | Day | Planned Min
Days Complete |  | Week 1 |  |  | 1 | 60
Days In Progress |  | Week 2 |  |  | 2 | 60
Days Not Started |  | Week 3 |  |  | 3 | 60
Total Days |  | Week 4 |  |  | 4 | 60
Completion % |  |  |  |  | 5 | 60
Total Planned Min |  |  |  |  | 6 | 120
Total Actual Min |  | Status | Count |  | 7 | 120
Total Actual Hours |  | Complete |  |  | 8 | 52
Total Planned Hours |  | In Progress |  |  | 9 | 59
|  | Not Started |  |  | 10 | 60
Week 1 Total |  |  |  |  | 11 | 60
Week 1 Done |  |  |  |  | 12 | 60
Week 2 Total |  |  |  |  | 13 | 79
Week 2 Done |  |  |  |  | 14 | 94
Week 3 Total |  |  |  |  | 15 | 55
Week 3 Done |  |  |  |  | 16 | 59
Week 4 Total |  |  |  |  | 17 | 58
Week 4 Done |  |  |  |  | 18 | 60
[5 empty] | 19 | 60
M0 Total |  |  |  |  | 20 | 102
M0 Done |  |  |  |  | 21 | 84
M1 Total |  |  |  |  | 22 | 49
M1 Done |  |  |  |  | 23 | 60
M2 Total |  |  |  |  | 24 | 51
M2 Done |  |  |  |  | 25 | 60
M3 Total |  |  |  |  | 26 | 60
M3 Done |  |  |  |  | 27 | 100
M4 Total |  |  |  |  | 28 | 85
M4 Done |  |  |  |  | 29 | 60
M5 Total |  |  |  |  | 30 | 106
M5 Done
M6 Total
M6 Done
M7 Total
M7 Done
M8 Total
M8 Done
M9 Total
M9 Done
Current Streak